## Slide 1
Data Migration Approach — Stateless & Stateful Waves
Stateless Waves 1-3
Stateful Waves 4-5
Cutover Wave 6
No Redis / Gemfire
STATELESS WAVES — No in-flight state. Safe to run parallel, no cutover risk. Roll back by pointing Kafka consumer group offset.
WAVES 1 → 3
W1
Batch Ingestion — Bronze & Silver Delta
Duration: 2-3 weeks · Risk: LOW
What migrates
• Kafka → Bronze Delta (S3)
• Silver filter + pre-validate
• 15min / 1hr / 1day triggers
• Stateless SQL transforms
State involved
None.
Pure read from Kafka.
No 24-48hr instate.
Offset = rollback.
Retire: Cloudera Hive (batch tables) · PySpark ETL jobs
▶ Parallel run: compare Bronze/Silver row counts vs Hive output. Switch when delta < 0.01%.
W2
Reference & Config State Migration
Duration: 3-4 weeks · Risk: LOW-MEDIUM
What migrates
• MongoDB config/format docs
• Regulator format templates
• LEI / instrument reference
• Counterparty maps + rules
Target (no Redis)
→ MongoDB → Lakebase Postgres
→ Broadcast vars in RTM
→ DynamoDB (hot config KV)
→ Delta tables + Unity Catalog
Retire: MongoDB (config + reference) · Gemfire/Redis reference caches
▶ Dual-read: app reads Lakebase first, falls back to MongoDB. Cut MongoDB when Lakebase stable 2 weeks.
W3
Batch Gold Pipeline + Job 2 Submission
Duration: 3-4 weeks · Risk: LOW-MEDIUM
What migrates
• Gold Delta transforms + lookups
• Job 2: SFTP/MQ/XML/Excel delivery
• DynamoDB config reads (Wave 2)
• gold.submissions_audit Delta
Prerequisite
Wave 2 complete.
All reference state in
Lakebase + DynamoDB
before Gold joins.
Retire: On-prem batch regulator submission · Hive gold tables · Spring Boot validity checker
▶ Shadow mode: cloud Job 2 posts to Regulator UAT endpoint only. Switch prod when UAT match > 99.9%.
STATEFUL WAVES — In-flight transaction state (24-48hr window). Requires seed strategy, cutover window, rollback plan.
WAVES 4 → 5
W4
RTM Transaction State — 24-48hr In-Flight Window
Duration: 6-8 weeks (includes 2-week parallel run) · Risk: HIGH · Requires cutover window
State Mapping
MongoDB instate (24-48h)
→ RocksDB ValueState seed
Gemfire/Redis hot KV
→ DynamoDB (no Redis target)
Hazelcast on-prem FCFS
→ Hazelcast Cloud CPMap
ElasticSearch instate
→ RocksDB MapState + DynamoDB
Seed Strategy
T-48h snapshot
Export MongoDB instate to DynamoDB snapshot. Script: mongo_export → dynamo_import.
RocksDB warm-up
On RTM first start: read 24-48h records from DynamoDB → seed ValueState/ListState before consuming Kafka.
Offset alignment
Set RTM Kafka consumer to T-48h offset. RTM replays and rebuilds full state from history.
Verify
Compare RocksDB state count vs MongoDB instate count before any live traffic.
Cutover Plan
1
Drain on-prem
Stop new trades entering on-prem pipeline. Flush in-flight. ~2min window.
2
Final snapshot
Last MongoDB/Gemfire instate export → DynamoDB. Delta from T-48h to now.
3
RTM warm start
RTM reads DynamoDB seed + replays Kafka from last on-prem offset.
4
Parallel verify
Run both 30min. Compare validated-trades output row-by-row.
Rollback: Kafka consumer group offset reset → on-prem resumes from same offset. DynamoDB snapshot preserved for re-seed.
Retire after Wave 4: Gemfire / Redis / Elasticsearch instate · On-prem Hazelcast · Spring Boot real-time filter
W5
Full RTM Live — SDP + Feedback Loop
Duration: 4 weeks · Risk: MEDIUM
Enable SDP Clusters B + C
• SDP Cluster B: DQ L3 + Hazelcast CPMap + IBM MQ live
• SDP Cluster C: feedback MQ → Kafka → RTM union()
• Hazelcast Cloud CPMap active (replaces on-prem HZ)
• DynamoDB replaces MongoDB for all runtime lookups
• Processed-trades → Delta gold tables via SDP-C
• gold.regulator_acks populated by feedback loop
State handover check
• Confirm RocksDB state stable across 48h window
• DynamoDB: submission status matches on-prem MongoDB
• Feedback acks round-trip latency < 2s
• SLA p99 < 7s for 3 consecutive trading days
Retire: MongoDB instate (24-48h) · On-prem Hazelcast · Spring Boot
Rollback: toggle SDP to shadow mode. On-prem resumes.
W6
Cutover & Decommission
Duration: 2 weeks · Risk: LOW (post-verify)
Go-live gates (all green)
5 trading days p99 SLA < 7s ✓
Regulator ack rate > 99.95% ✓
Zero duplicate submissions ✓
DQ failure rate < 0.1% ✓
Decommission sequence
1. Spring Boot (filter + validity)
2. PySpark (normalize)
3. Gemfire / Redis caches
4. MongoDB (config + instate)
5. Cloudera Hive cluster
6. On-prem Kafka brokers
7. On-prem Hazelcast cluster
Result: Single Databricks platform. 6 stacks → 1.
W1
Batch
Ingest
wks 1-3
W2
Reference
State
wks 3-6
W3
Batch Gold
+ Job 2
wks 5-8
W4
RTM
Txn State
wks 7-14
W5
Full RTM
+ Feedback
wks 13-16
W6
Cutover
+ Decommission
wks 15-17
◀── Stateless (W1-W3) ──▶
◀─── Stateful (W4-W6) ───▶
* Waves 2-3 and 3-4 overlap by ~1 week. Each wave has a defined rollback before advancing to the next.