## Slide 1
Data Migration Approach — Stateless & Stateful Waves (1/2)
Stateless W1-W3
Stateful W4-W5
No Redis · No Gemfire
STATELESS WAVES — W1 TO W3
No in-flight state · Safe parallel run · Rollback = Kafka consumer group offset reset
W1
Batch Ingestion — Bronze & Silver Delta
Duration: 2-3 weeks
LOW
What migrates
› Kafka → Bronze Delta (S3) — all messages
› Silver Delta — filter() + pre-validate DQ L1
› 15min / 1hr / 1day scheduled triggers
› Stateless SQL transforms only
State involved
None. Pure stateless read from Kafka. Rollback = Kafka offset reset.
✓ VALIDATION STRATEGY
Row count match
Cloud Bronze = on-prem Hive ± 0.01%
Schema match
Column names, types, nullability identical
DQ failure rate
Cloud Silver DQ fails ≤ on-prem fail rate
Promote gate
3 consecutive trading days all checks pass
🗑 Retire: Cloudera Hive batch tables · PySpark ETL jobs
▶ Parallel run: cloud reads same Kafka topic, separate consumer group. Zero impact on on-prem.
W2
Reference & Config State Migration
Duration: 3-4 weeks · Needs W1 stable
LOW-MED
State Mapping (no Redis · no Gemfire)
MongoDB config/format docs
→
Lakebase Postgres + DynamoDB
LEI / instrument reference
→
Delta tables + Lakebase broadcast vars
Counterparty maps + rules
→
DynamoDB hot KV + Unity Catalog
Gemfire / Redis ref caches
→
DynamoDB (no Redis target)
Target architecture
› Lakebase Postgres → regulator format templates, slow-changing rules
› DynamoDB → hot KV for runtime lookups (sub-ms)
› Delta + Unity Catalog → governance + ML-ready reference
› Broadcast vars in RTM → loaded from Lakebase on startup
✓ VALIDATION STRATEGY
Record count
Lakebase row count = MongoDB doc count
Spot-check
100 random records: field-by-field diff = 0
Lookup latency
Lakebase p99 lookup < 5ms
Promote gate
Dual-read stable for 2 weeks
🗑 Retire: MongoDB config/reference · Gemfire/Redis reference caches
▶ Dual-read: RTM reads Lakebase first, falls back to MongoDB. Cut fallback when Lakebase stable.
W3
Batch Gold Pipeline + Job 2 Submission
Duration: 3-4 weeks · Needs W2 stable
LOW-MED
What migrates
› Gold Delta: transformations + stream-static lookups
› Job 2: SFTP / IBM MQ / XML / Excel multi-format delivery
› DynamoDB config reads (migrated in Wave 2)
› gold.submissions_audit Delta table
Prerequisites
› ✅ Wave 2 complete — all reference state in Lakebase + DynamoDB
› ✅ Gold joins can resolve all lookups without MongoDB
› ✅ Job 2 reads DynamoDB configs successfully
✓ VALIDATION STRATEGY
Output record match
Cloud gold = on-prem Hive ± 0.01% per day
Shadow delivery
Job 2 posts to Regulator UAT endpoint only
Format validation
UAT ack rate > 99.9%, zero schema errors
Promote gate
UAT match 99.9% for 5 business days
🗑 Retire: On-prem batch regulator submission · Hive gold tables · Spring Boot validity checker
▶ Shadow: Job 2 posts to Regulator UAT only. On-prem continues prod submissions.
⚠ MongoDB → RocksDB Seed — Does it auto-sync after 48 hours?
Seed is one-time at Wave 4 startup: MongoDB instate (T-48h) → DynamoDB snapshot → RocksDB ValueState/ListState/MapState. Kafka offset set to T-48h so RTM replays full 48hr history.
After seed: No — RocksDB does NOT auto-sync from MongoDB. RocksDB is maintained by RTM consuming live Kafka events. Seeded records age out via 48hr TTL naturally, replaced by live event rebuilds. MongoDB and RocksDB diverge at T=0 by design.
Slide 1 of 2

## Slide 2
Data Migration Approach — Stateless & Stateful Waves (2/2)
Shadow Run W5-W6
Switchover W7
On-prem → Hot Standby → Decommission
STATEFUL WAVES — W4 TO W7
In-flight 24-48hr state · Seed strategy · Explicit primary/secondary switch · Decommission
W4
RTM Transaction State Seed & Parallel Run
Duration: 6-8 weeks incl. 2-week parallel run · Needs W2 stable
HIGH
State Mapping
MongoDB instate (24-48h)
→
RocksDB ValueState seed
Gemfire / Redis hot KV
→
DynamoDB (no Redis target)
Elasticsearch instate
→
RocksDB MapState + DynamoDB
On-prem Hazelcast
→
Hazelcast Cloud CPMap (audit W4)
Seed Strategy
1
T-48h snapshot
MongoDB instate + Gemfire KV → DynamoDB snapshot. Delta-only from T-48h window.
2
Kafka offset
Set RTM consumer to T-48h offset. Replay full 48hr event history before live.
3
RocksDB warm-up
RTM reads DynamoDB on startup → seeds Value/List/MapState before Kafka consume.
4
Verify counts
RocksDB state count vs MongoDB instate count — must match before any pipeline output.
Cloud does in W4
› Processes all trades from Kafka (separate consumer group)
› Runs full RTM Bronze → Silver → Gold pipeline
› Does NOT post to IBM MQ — no regulator submission
› Does NOT call Hazelcast CPMap for locking yet
› Writes output to cloud Delta tables for audit only
⚠ On-prem is PRIMARY. All regulator submissions from on-prem only.
✓ VALIDATION STRATEGY — Row-Level Diff
Trade count match
Cloud validated-trades = on-prem count ± 0.01%/day
Field-level diff
1000 trades/day: regulator-format fields identical
DQ flag alignment
Cloud DQ PASS/FAIL matches on-prem > 99.9% same trade_id
State consistency
RocksDB MapState exposure ± 0.1% vs MongoDB after 24h
SLA verification
Cloud RTM p99 latency < 200ms (no MQ cost yet)
Promote gate
All 5 checks pass for 5 consecutive trading days
↩ Rollback: Reset Kafka consumer group offset. DynamoDB snapshot preserved. On-prem unaffected throughout.
🗑 Retire after W4 gate: Gemfire / Redis / Elasticsearch instate · Spring Boot real-time filter
W5
Hazelcast Audit + Feedback Sync
Duration: 3-4 weeks · Cloud reads feedback from on-prem Kafka · Needs W4 gate
MED
Hazelcast Audit Table
Purpose: track row-level diff per trade_id between cloud and on-prem output
› Stored in Hazelcast IMap trade-audit:{trade_id} (NOT CPMap — no submission locking yet)
› Cloud writes: { cloud_validated, match: true/false, cloud_ts, onprem_ts, diff_fields }
› Confidence metric: % trades where cloud output matches on-prem today
› NOT used for FCFS submission — that is Wave 6
Feedback from On-Prem (cloud does NOT post)
› On-prem posts to Regulator (prod) as normal → receives ack/reject
› On-prem publishes ack to shared regulator-feedback Kafka topic
› Cloud SDP Cluster C consumes regulator-feedback Kafka topic
› Cloud updates gold.regulator_acks Delta + DynamoDB status
› Cloud RTM union() receives state_update events → RocksDB stays current
✓ VALIDATION STRATEGY
HZ audit match rate
Cloud output matches on-prem > 99.95%
Feedback sync lag
gold.regulator_acks lag vs on-prem < 30s
State divergence
RocksDB vs MongoDB delta < 0.05% after 48h
Promote gate
Audit match > 99.95% for 5 trading days
⚠ On-prem remains PRIMARY throughout W5. Cloud pipeline runs fully but submits nothing.
W6
Shadow Submission — UAT Endpoint
Duration: 2-3 weeks · Needs W5 gate green
MED
Enable cloud SDP Submission (UAT only)
› Enable Hazelcast Cloud CPMap.putIfAbsent — cloud now competes for FCFS lock
› Cloud winner posts to Regulator UAT endpoint only — NOT prod
› On-prem continues posting to prod endpoint unchanged
› Measure: % of trades where cloud wins FCFS vs on-prem, UAT ack rate, SLA
✓ Promote gate: UAT ack rate > 99.9%, zero schema errors, p99 SLA < 7s, 3 days stable
⚠ On-prem is still PRIMARY for prod throughout W6.
W7
Primary/Secondary Switch + Decommission
Duration: 2-3 weeks · Needs W6 go-live gates green
LOW
Cutover sequence
1
Switch prod endpoint
Cloud SDP → prod Regulator. On-prem demotes to UAT (hot standby).
2
Monitor 30 min
Compare prod ack rate, SLA, DQ — cloud vs standby. Anomaly → instant rollback.
3
Declare cloud PRIMARY
On-prem hot standby 2-4 weeks. Both consume Kafka, only cloud posts to prod.
4
Decommission
SB→ PySpark→ Gemfire→ MongoDB→ Hive→ on-prem Kafka→ on-prem HZ (sequential)
↩ Rollback: Flip cloud to UAT. On-prem standby resumes prod in < 2 min.
MIGRATION TIMELINE
W1
Batch
Ingest
Wks 1-3
W2
Reference
State
Wks 3-6
W3
Batch Gold
+ Job 2
Wks 5-8
W4
RTM State
Seed
Wks 7-14
W5
HZ Audit +
Feedback
Wks 13-16
W6
Shadow
Submit
Wks 15-17
W7
Switchover +
Decommission
Wks 17-20
Waves overlap by ~1 week at boundaries. Each wave requires a defined rollback gate before advancing.
Slide 2 of 2